## ToDos
Priority	Version	status	Where	Description
	0.9	close	ActivityItem	Change last Illustraion
	0.9	close	ActivityItem Click	Implement new feature "working for others" in short-press 3 times on item; / blue background instead of green background
low	0.9	open	ActivityScreen	Title
	0.9	close	ActivityScreen	3 click behavior, when close, when this feature is not possible
	0.9	open	ActivityScreen	optional shotlink icons for each category / Filter function
low	0.9	open	Calendar Item	Make Icons bigger
	0.9	close	Calendar Item / Editable Mode	@Thomas: What happend when an Acticity is deleted in the CalenderList? / Suggestion: add new TimeStamp with negative time
	0.9	close	Calendar View	Editable Button is displayed - it should be not displayed
high	0.9	open	Calendar View in / Editable Mode	Click behaviour of "+" and delet Item is in shortPress - it should be in longpress
high	0.9	open	CalendarView	Display 4 Days and record them
low	0.9	open	CalendarView	bad behavior - to much scrolling - tabs/buttons for each day
	0.9	open	CalendarView	Behavior of editble Activity - like food
high	0.9	open	CalendarView	Button for current date
low	0.9	open	CalendarView/ActivityView	Display current Time
	0.9	clsoe	Desktop	Implement Server to handle Connection to Smartphone
	0.9	open	LogFile	correct Excel sheet - true.-false - yes no? or nothing // delete option
	0.9	open	LogFile	correct File Structure
	0.9	open	LogFile	new Feature to combine many logfiles to on
	0.9	close	Main Activity	Test and extend Feature for dayswitch
	0.9	working	Settings	all relevant Variables displayed and editable
	0.9	close	Settings	Find a good place for hidden Settings Button
	0.9	open	Settings	Treshhold for When an Activity is shown in CalendarList
	0.9.	open	Settings	Click behavior change from - short to longpress
	0.9	open	Settings	Amount of parralel active activites editable
	0.9	open	Settings	enable Activity Shortlink Icon bar / Filter function
	0.9	open	Settings	Left side Navigation
	0.9	open	Settings	Editable App Screen off time
	0.9	open	Settings	Open and close Wifi connection automatily wehn open and close settingsmenü
	0.9	close	Settings/Connection	display and implement new feature send data to server - button in settings menu and function in app
	0.9	open	System	Explain current status of the system
high	0.9	open	Testing	Run the app more than 3 days
high	0.9	open	Testing	Save and reload current activity state
high	0.9	open	Testing	Save and reload current logfile
high	0.9	open	Testing	3 Days working
	0.9	open	Variables/ActivityView	Treshhold for When an Activity is shown in CalendarList
e	0.9	open	Variables/ActivityView	Check if logic is correct - when an activity is longer than 15min / - automatical add ti CanderaList

low	0.9	open	Logfile	more Values - Phase
	0.9	open	Logfile	more Values - amount of food
low	0.9	open	Logfile	more Value - Group
low	0.9	open	Logfile	more Value - sex
high	0.9	open	Logfile	more Value - error
	0.9	open	Connection	override activity file json

high	0.9	open	Loggging Function	Day change - wehn the day is changing - the active activities should be logged for the old day and activated a gain for the new day start 0:00:00
high	0.0	open	Loggging Function	Wehn the App will be closed than set a flag to the active activities

## Bugreport
	Bugreport

Priority	Version	What	Where	Behaviour
	0.9	App is crashing	Settings: Reset Button	When reset all Data while an Activity is active - App is crash
	0.9	Design Fix	CalendarList	First half hour is displayed "00:30" - it should be displayed "30"
	0.9	Logic	Activity Counter	Did not count propertly after 1:59 hours
	0.9	App is crashing	Settings: Reset Button	Wehn an activity is active and then press reset all - than the active activites are still there.
	0.9	Design Fix	LogFile	it dispalyes "0:2:30" instead of "00:02:20" - Workaround - calendar and substring
	0.9	Design	ActivityList	Wehn click on item then the Item is white and the activeList Item is green - bevor i edited some activity in editable mode
	0.9	Logic	Load App	Check load Json file why is the not existed activity there?
high	0.9	App System	System	When a long time the app was not usesed - like overnight - than the App is not reacting